## Test summary report
Tester | LMNghia, BLHoang
Date | 16-18/12/2025
Test Objective: | To verify that the functional requirements of the VietLedgr system meet the specifications and operate as intended for Administrator, Cashier Role, and Inventory management system.
Scope: | System-level functional testing (Black-box testing) + Limited Interface testing
Features to be Tested: | User Authentication (Login) for both Administrator and Cashier roles. Inventory Management (view, add, remove).
Test Environment: | OS: Windows 11 Home. Browser: Firefox (Version 146.0 (64-bit)). Device: Laptop (Ryzen 5500U, 16GB RAM).
Pass/Fail Criteria: | A test passes if the Actual Result matches the Expected Result defined in the test case.

## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
B001 | getBatch() API error | getBatch() API error: Cannot call get_product() | UC03 | Critical | BLHoang | 16/12/2025 | Closed
B002 | Login as Cashier led to a 404 page not found | Login as Cashier led to a 404 page not found. | UC02 | High | LMNghia | 18/12/2025 | Open
B003 | Cannot delete a product | Cannot delete a product using Inventory/Product screen. When click the button, nothing happen, and backend did not register any request. | UC03 | Medium | LMNghia | 18/12/2025 | Open | Probably front end problem
B004 | Cannot add product | Cannot add a product using Inventory/Product screen. When click the button, the product detail screen did pop up. After filling all the information and click to confirm, nothing happen. The backend did register the request, but investigation on the database show no modification. | UC03 | Medium | LMNghia | 18/12/2025 | Open | Probably back end problem
B005
Note on D1: Function ID of the function where the defect is found
Note on E1: High, Medium, or Low
Note on F1: Name of the tester who reports the defect
Note on H1: Open or Closed